## Action Item
Item | Area of Focus | Goal / Objective | Progress/Accomplishment | Dependency | Responsible | Activity Type ( Committed - C Perhaps - P) | Priority | Status | Due Date | Actual Date
1 | Applications | Main CGRS - The executable is complete, with an engineering quality user interface. It connects with both the RSA and the Vent. It demonstrates the full ability to move data from one end to the other. It launches separate executables for the Release Notes/Doc Viewer, Log Viewer and Software Updater |  |  | ALL |  |  |  | 2012-08-14
2 | Applications | Release Notes / Document Viewer - The executable launches with args provided by the Main CGRS. It establishes connectivity with the RSA. It provides some form of access to the document content - either for download or viewing directly. |  |  | Boyer / Batch |  |  |  | 2012-08-07
3 | Applications | Log Viewer - The executable launches with args provided by the Main CGRS. It establishes connectivity with the RSA. It makes one or more logs presentable (full featured, but possibly with mock enum strings) and the remainder of the logs displayed in raw hex. There is no "cursor" / paging functionality at this time for large files. |  |  | Boyer |  |  |  | 2012-08-14
4 | Applications | Software Updater - The executable launches with args provided by the Main CGRS. It establishes connectivity with the RSA and the Vent. It performs a software update to the vent (or vent mock object). |  |  | Ekaireb / Boyer |  |  |  | ???
5 | UI | A story board is presented to the Service Organization illustrating the UI features that will be developed. |  |  | Richard Batch |  |  |  | 2012-08-07
6 | Vent/VentIF | When in service mode, the PB980 Ventilator is able to respond to a REST api call to get Device Information. 1) Ventilator webserver moved to line interface1. 2) Webservice to get DeviceInfo. 3) PC Driver interface to interact with the ventilator to get DeviceInfo. |  |  | Michael Ekaireb |  |  |  | 2012-07-24
7 | Vent/VentIF | The download API provides the capability to set the downloader’s working path and use a manifest provided in a notification. |  |  | Michael Ekaireb |  |  |  | 2012-07-31
8 | Vent/VentIF | When in service mode, the PB980 Ventilator is able to respond to a REST api call to get Logs. |  |  | Michael Ekaireb |  |  |  | 2012-08-07
9 | Vent/VentIF | When in service mode, the PB980 Ventilator is able to take download and install software updates |  |  | Michael Ekaireb |  |  |  | ??? |  | is this essentially the same as line #8?
10 | RSA Interface | The serializer/deserializer is updated to incorporate schema changes that have been made during implementation of the Remote Service Agent. |  |  | Michael Ekaireb |  |  |  | 2012-07-24
11 | RSA Interface& Mock UI | The framework needed to establish a session and login to the Remote Service Agent using a Mock Login dialog is complete. A Mock Login dialog is available to test the login. 1) Establish a session and login to the Remote Service Agent. 2) Mock Login UI |  |  | Robert Boyer |  |  |  | 2012-07-24
12 | RSA Interface& Mock UI | A basic execution shell is created and is able to get notifications form the Remote Service Agent and display them in a Mock UI in a notification view. 1) Get info from RSA, launch exe, rm old notices. 2) Complete Mock UI, include notification view. |  |  | Robert Boyer |  |  |  | 2012-07-31
13 | RSA Interface& Mock UI | Device Availability is detected and displayed in the UI. |  |  | Robert Boyer |  |  |  | 2012-08-07
14 | RSA Interface | When a device is detected, device identifying information is pushed to the Agent. |  |  | Robert Boyer |  |  |  | 2012-08-07
15 | RSA Interface& Mock UI | A Mock UI is created and integrated with the Ventilator Interfacing API to get logs and push the log data to the Agent |  |  | Robert Boyer |  |  |  | 2012-08-14
16 | RSA | RSA provides a "Resource Type" document | [6 empty] | 2012-07-31
17 | Tools | Tool created/used to inject resource documents into the CGRS server | [6 empty] | 2012-08-07
18 | RSA Interface& Mock Log UI | Log Viewer code able to query RSA for resource files. 1) Log Descriptor 2) Enum to String List |  |  | Robert Boyer |  |  |  | 2012-08-14

## Whiteboard
Subsystem | Goal | Date Est | Item in Goals tab
RSA | Covidien exercise laptop agent interface. | 2012-07-20 | 5
RSA | Resync w/ new changes to Agent XML | 2012-07-24 | 5
RSA | Resync w/ new changes to support expunge, mailboxinfo requests. | 2012-07-27 | ???
Ctrl | Establish a session with the RSA. * Login * Session | 2012-07-24 | 5
Ctrl | Get info from RSA, launch exe, rm old notices. | 2012-07-31 | 6
Ctrl | Update Serializer/Deserializer to new schema. | 2012-07-24 | 2
Ctrl | Release Notes | 2012-08-07 | 11
Ctrl | Push logs to agent | 2012-08-14 | 9
Ctrl | Push device info | 2012-07-24 | 3
Ctrl | Device Availability | 2012-08-07 | 1
UI | Storyboard from Richard | 2012-08-07 | 10
Mock UI | Mock LOGIN screen. | 2012-07-24 | 5
Mock UI | Complete mock UI, include notification view. | 2012-07-31 | 6
Mock UI | Release Notes View | 2012-08-07 | 11
Mock UI | Display logs in hex | 2012-08-14 | 9
Mock UI | Device Availability | 2012-08-07 | 1
Vent/VentIF | DeviceInfo & connectivity to ventilator webservice. Note:Config file with connectivity releated information. | 2012-07-24 | 4
Vent/VentIF | Integrate downloader w/ controller | 2012-07-31 | 8
Vent/VentIF | Binary logs(Cust. Agent) | 2012-08-07 | 7
Vent/VentIF | User readable logs + log curser. (Cust. UI) | 2012-08-20 | 12
Action Item | Will need to revisit interface between vent and PC to support a centralised solution.
Action Item | Update header for notification to include MIME type.
Action Item | Add the concept of metadata element to the header of a notificaion.
Action Item | Robert to review notification schema to find best approach to incoperate, Actions Human readable HTML/txt. Binary blob data. The assumption is that the controller is going to inflate the notification based on type with an Actions list, UI Text ,and CDATA.
Action Item | Talk to John about bringing back the getdevicelist command to the agent.
Action Item | Discuss w/ John why we need to provide the ability to enter in a serial number in the UI.
Action Item | Sid expects a HLD Arch design document. |  | ???
Action Item | Sid expects integration Plan+Milestones that we will publish to the external team. | 2012-07-20
Tabled Discussion | Should we be able to view a log that captures the interactions between the Agent and the RSA.
Action Item | Provide Richard an API and UI spec. Note: Robert to be interface between team and Richard for UI development.
Action Item | Dr. Boyer and Michael need access to the source for the Agent.